Module 7 - Project management for sustainable development

IO1 – OUTSIDE Toolkit for Teachers

Session 3 - How to manage a green project

TEMPLATE 7c part A

IIS Fermi – ASD Trekkify

Given the template 7c part A, the trainer asks the teams to identify:

- the project timeline

- the potential risks

- expenses and estimate budget

- the main internal and external stakeholders of their project

SCENARIO A – planning the end of the school year party

SCENARIO B – organizing your best friend birthday

SCENARIO C – planning your summer vacation

SCENARIO D – organizing the fundraising for cleaning up the school area

Students are given 45 minutes to discuss together and sum up the results of the discussion by filling in the table on the next page. The appointed communication officer takes notes and prepares a few slides for the project presentation that will happen at the end of the 4 sessions.

PROJECT TIMELINE (GANTT CHART)

| Activities/tasks | Responsible | Weeks/months |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 1.1 book a meeting with the school principal | Project manager |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 organize a meeting with the teachers | Project manager |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 identify the rooms/areas of the school to be used during the event | Project team |  |  |  |  |  |  |  |  |  |  |  |  |

RISK MANAGEMENT PLAN

| Risk type Select the risk type: management; technical; organizational; external; communicational | Outcome Describe the possible outcome for the risk identified | Rating Identify the rating: low, medium, high, extreme | Likelihood Identify the likelihood: low, medium, high | Proposed actions to mitigate the risks Describe the proposed actions: | Risk owner Indicate the team member responsible for monitoring the risk |
| --- | --- | --- | --- | --- | --- |
| Ex. Rain - External | Not being able to use outdoor spaces | High | Medium | Think of a plan B and be ready to carry out the event indoor | Project manager |

FINANCIAL PLANNING

| COSTS |  |  |  | INCOME |  |  |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expenses type Identify your expense type: material, equipment, travel, accommodation, food & beverage, services, other | Expense description List all the foreseen expenses | Cost estimation Estimate a cost for each expense item |  | Income type Identify your income type: sponsors, participants contribution, investors, own funding, public funding, other | Income description List all the foreseen expenses | Income estimation Estimate the income value |  |  |
| Ex. food and beverage | Catering for 200 people | 3000€ |  | Participants’ contribution | Families’ contribution | 20€ per student |  |  |
| TOTAL: |  |  |  | TOTAL: |  |  |  |  |

STAKEHOLDERS REGISTER

| Stakeholder name | Stakeholder type Internal/external | Interest low, medium, high | Impact low, medium, high | Expectation Describe what is expected from the stakeholders | Comms requirements Indicate communication channel and the contact |
| --- | --- | --- | --- | --- | --- |
| Ex. Jim’s catering | External | low | Medium | Provide catering service for the party | Email/ phone |
| Ex. Jonh Doe (school principal) | Internal | High | High | Allow the party to happen, approval of the plan | F2F meeting |